Date: 6/08/2021 **Notice**

All BE ETRX students are informed to follow the project schedule:

| **SN** | **Date** | **Task** | **Remark** |
| --- | --- | --- | --- |
| 1 | 10-08-2021 | Submission and finalization of Project Title | 1. Concern with the project guide.  2. Finalize the Project Title.  3. Project guide should ensure the appropriateness of Project Title.  4. Late submission will not be entertained. |
| 2 | 7-9-2021 | Project review –I presentation | 1. Prepare presentation of Project.  1.1 Abstract/ problem definition   * 1. Introduction   2. Literature review.   1.4 Expected throughput & Conclusion  1.5 References  2. PPT should be approved by Project guide before  presentation  3. Make sure that the PPT validates the Project Title. |
| 3 | 5-10-2021 | Project review –II by Industrial Experts. Presentation  1. Complete Architecture  2. Complete Analysis | 1. Student should complete the architecture of Project.  2. Prepare presentation of Project.  2.1 Abstract/ problem definition  2.2 Introduction  2.3 Literature review  2.4 Methodology   * 1. Flow of project (block dia & circuit Dia)   2. Advantage ,Disadvantage, Future scope &   Conclusion  2.7 References  3. PPT should be approved by Project guide before  presentation  4. Complete the analysis of Project and submit the report to guide. |
| 4 | 12-10-2021 | Submission of Synopsis | 1. Project report should have  1.1Abstract/ problem definition  1.2 Introduction  1.3 Literature review   * 1. Methodology   1.5 Flow of project (block dia & circuit Dia)  1.6 Advantage ,Disadvantage, Future scope &  Conclusion  1.7 References  2. Project report should be approved by Project  guide before final submission |

**Project Coordinator APC HOD**

Mrs.R.V.Chimankare Mrs.V.A.Pande Dr.B.G.Hogade

**Note:**

**1) Update your work in the Project work data sheet every week.**

**2) Term Work (50)** = Attendance (10M) + Average of Project Review I& II per group (20M)

+EPIC(10M)+Project competition + Internship paper presentation (10M)